## workbook builder
DEVELOPING YOUR PROJECT WORKBOOK
This is a tool to help build your Results Framework, Workplan, Risk Register and Learning for your Gavi grant. The tool takes you through a simple process of: • Identifying your main project activities and relating these to short-medium changes you hope to see (Results Framework); • Recording these activities and planning timeframes (Workplan); and • Working through your assumptions and possible project challenges (Risk Register). Completing this workbook will ensure there is a clear logic and flow of how you see change happening as a result of your project. The purpose of the workbook is to help articulate your project design into a Results Framework, Workplan and Risk Register, which will be used for reporting each quarter. The final tab of this workbook is for capturing your learning throughout the project (Learning). As you develop your project workbook, consider what you would like to learn and feed back.
Problem Statement:
Limited healthcare infrastructure, coupled with vaccine hesitancy driven by cultural and social factors has contributed to lower vaccination coverage in Balochistan.
Project Goal:
We aim to increase vaccination coverage up to 90% by implementing rigorous demand generation strategies and ensuring the sustainable uptake of vaccinations for children aged 0-23 months, with a focus on eliminating gender and equity gaps.
PROJECT ACTIVITIES
| # | Activity | Assumptions
| 1 | Hiring and management of staff Hiring of staff of SRs(Project coordinator, community moblizers and admin Finance officer) | Availability of skilled personnel in remote areas. Timely recruitment and retention of staff, especially in underserved areas. Adequate support and training to ensure effective performance. Availability of office space for project staff. Stable security and political situation.
| 2 | Project orientation training including PSEAH of staff | Availability of skilled personnel & resource persons in remote areas. Availability of adequate training space Stable security and political situation.
| 3 | Community Moblization and Engagement for demand generation in underserved areas Demand generation activities for enhancing the knowledge and improving the practices of the communities for utilization of EPI services Community Engagement events including Elected Representatives, Community Elders total 16 Community engagement event with elected presentative and community elders and important stakeholders. 1 event Quarterly with important stakeholders at District level and 1 event at Tehsil level monthly will be conducted by Azat Foundation district team. In each event 20-30 participant will be engaged. | Availability of skilled community resource persons Availability of community members for sessions Availability of space for the activities
| 4 | Awareness raising sessions through Community Resource Persons (CRPs) and social organizers: 04 Social Organizers (02 males, 02 females) with the help of CRPs will organize & conduct awareness raising sessions at community level. They will conduct 08 sessions per month per UC with minimum 10 participants in each session. | Availability and willingness of community members to particpate in sessions Availability of IEC and other Materials for the sessions Effective communication strategies to address misconceptions about immunization. Stabel safety & security situation adequate resources for Training of staff
| 5 | Social Media Campaign (WhatsApp & Facebook): Sharing of IEC materials through social media campaigns in district Jhalmagi Messages on importance of Vaccination and immunization to be dessiminated through social media Information on vaccination camps will be dessinimated at their UC and villages level so that all caregivers can vaccine their children at Health facilities and vaccination camps in their respective areas. | Community Access to Mobile Phones and Internet Widespread Use of Social Media Platforms support of local stakeholders in circulation and reinforcement of key messages through their networks and WhatsApp groups. No Major Social Media Disruptions
| 6 | Vaccination/ Mobile Camps: With support of CRPs, Vaccination camps at UC & villages level for the vaccination of children age 0-23 months. Monthly 10 vaccination camp will be conducted in 13 UC of JhalMagsi. In total 1430 Vaccination camps will be conducted during the project time. The number of camps may vary depending on the Government's micro-plan vaccination schedule | Uninterrupted Government Coordination (Government’s EPI micro-planning and vaccination schedules changes or delays can disrupt the planned number of camps) Effective coordination with local communities and leaders to foster trust. Adequate vaccine supplies, cold chain equipment, and related logistics Community acceptance and participation
| 7 | Coordination with Govt. Officials | Effective coordination with government health department Presence of all required government staff Presence of all participants for coordination meetings Stabel safety & security situation | Keep track of your assumptions as you go.
| 8 | Monthly /quarterly progress review meeting | Availability and responsivenss of all concerned officials for meetings Stabel safety & security situation not hampering staff movements Ability to organize periodic meetings as per schedule Continued Government Support and Cooperation
| 9 | Monitoring Visits M&E reports | Availability of accurate and timely data collection tools. Active participation of staff in field in reporting data. Adequate resources for ongoing monitoring and evaluation activities. Stabel safety & security situation for field travel

## RFW
Results Framework (Output-Level – aligned with grant indicators)
Organization | Azat Foundation
Project Name: | Address barriers to immunization and contribute to increasing immunization coverage in Balochistan for zero-dose and under immunised children and missed children.
Project District | Jalmagsi
Project Duration | 21 Months
Impact | Increased immunization coverage and reduced vaccine-preventable diseases in Jhal Magsi.
Outcome | Vaccination services are effectively integrated into PHC delivery across 13 UCs.
Outputs | Indicators | Six month target | Six month actual | 12-month target |  | 12-month actual |  | 18-month target |  | 18-month actual |  | 24 Month target |  | 24 month actual |  | Final target | Final actual | Means of verification
|  | Add a target for the first 6-months of your project. July to Dec 2025 | Complete this in the first six-month reporting period, after 6 months of project implementation. | Add a unique target, including what you want to achieve in months 7-12 ONLY (Jan to June 2026) | Add a cumulative target, including what you want to achieve in months 0-12 | Add your unique result from months 7-12 of implementation, complete this in your second six-month reporting period | Add your cumulative result from months 0-12 of implementation, complete this in your second six-month reporting period | Add a unique target, including what you want to achieve in months 13-18 ONLY (July to Dec 2026) | Add a cumulative target, including what you want to achieve in months 0-18 | Add your unique result from months 13-18 of implementation | Add your cumulative result from months 0-18 of implementation, complete this in your final reporting period | Add a unique target, including what you want to achieve in months 19-24 ONLY (Jan to March 2027) | Add a cumulative target, including what you want to achieve in months 0-24 | Add your unique result from months 19-24 of implementation, complete this in your final reporting period | Add your cumulative result from months 0-24 of implementation, complete this in your final reporting period | Add your final target. | You will fill this in the final reporting period. | Write here how you plan to verify the progress that has been achieved.
1. Coordination with Govt. and stakeholders enhanced | # of coordination meetings held with district officials | 6 | 6 | 6 | 12 | 6 | 12 | 6 | 18 |  | 0 | 3 | 21 |  | 0 | 21 |  | Meeting minutes, government coordination reports, signed attendance sheets across 13 UCs (Gandawah, Hathyari, Safrani, Barija, Akbar Abad, Mat Sindhur, M/C Jhal Magsi, Saifabad, Patri, Khari, Panjuk, Aqil Jagirani, Fatehpur)
2. Community awareness on vaccination improved | # of awareness sessions held with CRPs/social organizers | 2860 | 2860 | 2860 | 5720 | 434 | 5720 | 2860 | 8580 |  | 0 | 1430 | 10010 |  | 0 | 10010 |  | CRP session registers, monthly mobilization reports across 13 UCs (Gandawah, Hathyari, Safrani, Barija, Akbar Abad, Mat Sindhur, M/C Jhal Magsi, Saifabad, Patri, Khari, Panjuk, Aqil Jagirani, Fatehpur)
| # of care givers, parents, community members attended the awareness sessions | 28600 | 28600 | 28600 | 57200 | 4613 | 57200 | 28600 | 85800 |  | 0 | 14300 | 100100 |  | 0 | 100100 |  | Session attendance sheets with gender breakdown, CRP activity logs across 13 UCs
3. Community engagement sessions conducted | # of engagement sessions with community elders/reps | 8 | 8 | 8 | 16 | 8 | 16 | 8 | 24 |  | 0 | 4 | 28 |  | 0 | 28 |  | Advocacy event reports, signed attendance, photographs across 13 UCs
4. Access to vaccination improved through mobile/outreach | # of mobile vaccination camps organized | 716 | 716 | 714 | 1430 | 924 | 1430 | 715 | 2145 |  | 0 | 357 | 2502 |  | 0 | 2502 |  | Camp registers, Excel upload logs, vaccinator signatures across 13 UCs (Gandawah, Hathyari, Safrani, Barija, Akbar Abad, Mat Sindhur, M/C Jhal Magsi, Saifabad, Patri, Khari, Panjuk, Aqil Jagirani, Fatehpur)
| # of zero dose / defalters/on sheduled & refusals hildren identified and vaccinated | 2500 | 2500 | 2500 | 5000 | 3697 | 5000 | 2500 | 7500 |  | 0 | 1250 | 8750 |  | 0 | 8750 |  | EPI vaccination registers, screening cards, database records from all 13 UCs
5. Digital & social awareness enhanced | # of WhatsApp/FB posts developed and shared | 780 | 780 | 780 | 1560 | 780 | 1560 | 780 | 2340 |  | 0 | 390 | 2730 |  | 0 | 2730 |  | Social media campaign screenshots, broadcast group logs, analytics reports
6. Effective project monitoring | # of support , supervision and mangment monitoring visits conducted | 12 | 12 | 12 | 24 | 12 | 24 | 12 | 36 |  | 0 | 6 | 42 |  | 0 | 42 |  | Field monitoring reports, supervisor checklists, visit logs across 13 UCs
7. Reporting compliance | % of reports submitted on time | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 0 | 100% | 100% |  | 0 | 100% |  | Monthly and quarterly reports, donor submission receipts

## Workplan monthly Q targets
Detailed Impelementation Plan
|  | Organization | Azat Foundation
|  | Project Name: | Address barriers to immunization and contribute to increasing immunization coverage in Balochistan for zero-dose and under immunised children and missed children.
|  | Project District | Jalmagsi
|  | Project Duration | 21 Months
Project Work plan for “Integration of vaccination services at PHC level leveraging existing operational sites” Project Jhal Masi
ANNEX A | S. NO | Key Activities | Lead Party | Responsibility | Total Targets | 1st Quarter |  |  |  | 2nd Quarter |  |  |  | Six months Target (July to Dec25) | 3rd Quarter |  |  |  | 4th Quarter |  |  |  | Six months Target (July to Dec25) | Annual Targets
Ref | [5 empty] | Q.1 Targets | July | August | Sept | Q. Targets | Oct | Nov | Dec |  | Q. Targets | Jan | Feb | March | Q. Targets | April | May | June
1.1 | 1 | Hiring of staff | Azat Foundation | HR | 1 | 1 | 1 |  |  | 0 |  |  |  | 1 | [8 empty] | 0 | 1
| 2 | Orientation of Staff on project | Azat Foundation | Program team | 1 | 1 | 1 |  |  | 0 |  |  |  | 1 | [8 empty] | 0 | 1
| 3 | Coordination with Govt. Officials | Azat Foundation | Project Coordinator/ M&E | 12 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 6 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 6 | 12
| 4 | NOC acquisition from authorities | Azat Foundation | Project Coordinator/ M&E | 1 | 1 | 1 | [6 empty] | 1 | [8 empty] | 0 | 1
1.2 | 5 | Vehicle hiring | Azat Foundation | Admin | 2 | 2 | 2 | [6 empty] | 2 | [8 empty] | 0 | 2
1.3 | 6 | Field office establishment | Azat Foundation | Admin | 1 | 1 | 1 | [6 empty] | 1 | [8 empty] | 0 | 1
1.4 | 7 | Purchase of laptop and Printer | Azat Foundation | Admin | 1 | 1 | 1 | [6 empty] | 1 | [8 empty] | 0 | 1
1.5 | 8 | Staff registration with EOBI | Azat Foundation | HR/ Finance | 1 | 1 | 1 | [6 empty] | 1 | [8 empty] | 0 | 1
2.1 | 9 | One day refresher for Vaccination | Azat Foundation | Project Coordinator/ M&E | 1 | 1 | 1 | [6 empty] | 1 | [8 empty] | 0 | 1
2.2 | 10 | Monitoring visits | Azat Foundation | M&E AF | 24 | 6 | 2 | 2 | 2 | 6 | 2 | 2 | 2 | 6 | 6 | 2 | 2 | 3 | 6 | 2 | 2 | 2 | 12 | 24
2.3 | 11 | Social media campaign (Whatsapp & FB) | Azat Foundation | Azat Foundation team | 1560 | 390 | 130 | 130 | 130 | 390 | 130 | 130 | 130 | 390 | 390 | 130 | 130 | 390 | 390 | 130 | 130 | 130 | 780 | 1560
2.4 | 12 | Vaccination & Mobile camps | Azat Foundation | PC, Social mobilization | 1430 | 358 | 119 | 119 | 120 | 358 | 119 | 119 | 120 | 357 | 357 | 119 | 119 | 357 | 357 | 119 | 119 | 119 | 714 | 1430
2.5 | 13 | Community Engagement Incl Elected Representatives, Community Elders. | Azat Foundation | PC, Social mobilization | 16 | 4 | 2 | 1 | 1 | 4 | 1 | 2 | 1 | 4 | 4 | 2 | 1 | 4 | 4 | 2 | 1 | 1 | 8 | 16
2.6 | 14 | Awareness Raising Session CRP & scoial organizers. | Azat Foundation | Mobilization and CRPs team | 5720 | 1430 | 476 | 478 | 476 | 1430 | 476 | 478 | 476 | 1430 | 1430 | 476 | 478 | 1430 | 1430 | 476 | 478 | 476 | 2860 | 5720
1 | 15 | Monthly reporting | Azat Foundation | Project Coordinator/ M&E | 12 | 3 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 6 | 12
| 16 | Quarterly reporting | Azat Foundation | Project Coordinator/ M&E | 4 | 1 |  |  | 1 | 1 |  |  | 1 | 1 | 1 |  |  | 1 | 1 |  |  | 1 | 2 | 4
| 17 | Project completion Report | Azat Foundation | Azat Foundation | 1 | [8 empty] | 0 |  |  |  |  | 1 |  |  | 1 | 1 | 1

## Workplan
WORKPLAN
Organization |  | Azat Foundation
Project Name: |  | Address barriers to immunization and contribute to increasing immunization coverage in Balochistan for zero-dose and under immunised children and missed children.
Project District |  | Jalmagsi
Project Duration |  | 21 Months
Project Goal (outcome) |  | We aim to increase vaccination coverage up to 90% by implementing rigorous demand generation strategies and ensuring the sustainable uptake of vaccinations for children aged 0-23 months, with a focus on eliminating gender and equity gaps.
# | Activities |  | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 13 | Month 14 | Month 15 | Month 16 | Month 17 | Month 18 | Month 19 | Month 20 | Month 21 | Total activiites
|  | Sub activities | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01
1 | Prepration | Hiring of staff | bar: 2025-07-01
Orientation of Staff on project | bar: 2025-07-01
Coordination with Govt. Officials | bar: 2025-07-01 to 2027-03-01
NOC acquisition from authorities | bar: 2025-07-01
Vehicle hiring | bar: 2025-07-01
Field office establishment | bar: 2025-07-01
Purchase of laptop and Printer | bar: 2025-07-01
Staff registration with EOBI | bar: 2025-07-01
2 | Community Moblization and Engagement | Community Engagement Incl Elected Representatives, Community Elders. | 1 | 1 | 1 | 1 | 2 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 2 | 1
3 | Awareness Raising | Awareness Raising Session CRP & scoial organizers. | 1 | 478 | 476 | 476 | 478 | 476 | 476 | 478 | 476 | 476 | 478 | 476 | 476 | 478 | 476 | 476 | 478 | 476 | 476 | 478 | 476
4 | Social Media Compaign | Social media campaign (Whatsapp & FB) | 1 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130 | 130
5 | Response/support | Vaccination & Mobile camps | 2025-07-01: 1; 2025-08-01: 119; 2025-09-01: 120; 2025-10-01: 119; 2025-11-01: 119; 2025-12-01: 120; 2026-01-01: 119; 2026-02-01: 119; 2026-03-01: 119; 2026-04-01: 119; 2026-05-01: 119; 2026-06-01: 119
6 | MEAL activities | Monitoring visits | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
7 | Reporting | Monthly reporting | bar: 2025-07-01 to 2027-03-01
Quarterly reporting | bar: 2025-09-01; 2025-12-01; 2026-03-01; 2026-06-01 to 2027-03-01
Project completion Report | bar: 2026-06-01 to 2027-03-01

## Risk register
RISK REGISTER
Project Goal (outcome) | We aim to increase vaccination coverage up to 90% by implementing rigorous demand generation strategies and ensuring the sustainable uptake of vaccinations for children aged 0-23 months, with a focus on eliminating gender and equity gaps.
Organization | Azat Foundation
Project Name: | Address barriers to immunization and contribute to increasing immunization coverage in Balochistan for zero-dose and under immunised children and missed children.
Project District | Jalmagsi
Project Duration | 21 Months
Instructions: Please enter one project-based risk per row. Consider governance, safeguarding, context, operational, programmatic, reputational, financial and fiduciary risks and write specific risks (for example: a demonstration on June 5th might not allow the CHW to get to province XYZ and thus prevent from distributing vaccines. A mitigation strategy is to reschedule visits to that area if the demonstration is confirmed). Refer to your safeguarding policy and any other relevant risk-related documents. Then think about your assumptions in the Workbook builder tab and ensure they are covered here. Refer to the Grantee Guidance for more information. Include at least two safeguarding risks.
Date added | Risk type | Description of risk | Probability | Impact |  | Action | Quarterly changes | Did the risk materialise?
| Please select a risk type (choose from dropdown menu) | Include the cause of the risk, the risk itself, and the impact of the risk | How likely is it this risk will materialise? (choose from dropdown menu) | What would happen if this risk materialised? | Risk magnitude | What actions will you take to mitigate this risk? | Has anything changed this quarter? | What happened?
| Operational | Vaccine stockouts at health facilities | Medium | Immunization activities would be interrupted or delayed, reducing vaccination coverage and undermining project goals, potentially leading to disease outbreaks. | High | Coordinate monthly with EPI focal person for stock forecasts and replenishment | Q2: Risk is now closed Q1: We have built a relationship with two teachers who play a key role in the community and are highly respected. We believe this will help mitigate disruptions during potential school closures. | The schools did close due to floodings, but only for 2 weeks. Since we had built a relationship with 2 key teachers before the closures, we kept in touch during the closures and found it easy to continue school and teacher-related activities once schools reopened.
| Security | Local conflict or unrest hampers field activities | Low | Suspension or cancellation of outreach sessions, staff safety compromised, and delays in implementation timelines. May also damage community trust. | High | Engage with local elders; plan flexible schedules; real-time monitoring
| Financial | Delays in fund disbursement from IHHN | Medium | Disruption in project operations such as staff payments, procurement, and activity execution. May result in loss of momentum and lower community participation. | Medium | Timely reporting and fund utilization; follow-up with Grants Manager
| Human Resource | High staff turnover of social organizers or vaccinators | Medium | Program continuity and quality would suffer, leading to inconsistent delivery, loss of community rapport, and increased training and onboarding costs. | Medium | Develop standby staff pool; refresher trainings
| Community Acceptance | Misinformation leading to low participation in sessions or camps and cause refusal | Medium | Target populations may avoid services due to fear or misunderstanding, drastically lowering coverage and impact. May also increase resistance and hesitancy. | High | Use community leaders, CRPs, and social media to build trust
| Procurement | Delay in procurement due to thresholds and approvals | Medium | Program inputs (supplies, materials, services) will arrive late, hindering implementation and possibly increasing costs due to last-minute purchasing or emergency procurement. | Medium | Maintain procurement plan aligned with IHHN policy; pre-approval process in place
| Compliance | Incomplete documentation or reporting | Low | Weak data quality can lead to poor decision-making, donor non-compliance, and reduced credibility. It may also hinder timely fund release or project continuation | High | Use IHHN formats; conduct internal quality checks
July 2026 | Security / Contextual | Regional security instability, localized law and order challenges, or inter-tribal friction impeding field team movement to remote UCs (e.g. Khari, Panjuk, Aqil Jagirani). | Medium | High | High | Engage local community elders, tribal influentials, and District Administration for early clearance; adopt flexible mobile camp scheduling and real-time security tracking across all 13 UCs. | New risk added for extension phase (July 2026 – March 2027). | Continuous field security monitoring active; alternative mobile routes pre-planned.
July 2026 | Operational / Environmental | Monsoon flash flooding and extreme summer heat causing road washouts and access blockades in low-lying UCs of Jhal Magsi, delaying mobile outreach camps. | Medium | High | High | Pre-position CRPs and mobile teams in high-risk UCs; coordinate emergency mobility with District Health Authorities; reschedule mobile camps during severe weather alerts. | Added for extension phase monsoon & summer operations. | Weather tracking active; field logistics adjusted accordingly.
July 2026 | Programmatic / Supply Chain | Potential delays or stockouts of routine EPI vaccines and cold-chain carrier equipment at government health facilities during the extension period. | Medium | High | High | Maintain regular stock forecasting and monthly coordination meetings with DHO and EPI focal persons; utilize passive vaccine carrier cold boxes during outreach. | Added for extension period vaccine supply chain assurance. | Monthly stock forecasts shared with DHO office.

## Learning
LEARNING
Organization | Azat Foundation
Project Name: | Address barriers to immunization and contribute to increasing immunization coverage in Balochistan for zero-dose and under immunised children and missed children.
Project District | Jalmagsi
Project Goal (outcome)
Instructions: As you carry out your project, you will be learning what is effective; what is happening in context; who is affected; how activities are benefitting certain participant groups; what isn't working well; what you need to adjust; how the project should adapt; how and if your team is growing, etc. Please use this sheet to capture 1 - 3 of your own learning questions. Consider gender equality and social inclusion (GESI) in your learning. Refer to the Grantee Guidance document for ideas on completing this section.
Learning area | Learning Question |  |  | Use and dissemination of learning | Progress tracker
| Develop key learning questions to: 1. Test, explore and learn from your underlying assumptions 2. Fill gaps in your technical knowledge and understanding to ensure sound technical approach 3. Identify game changers, open doors and break glass ceilings. | How to Collect Information | When to Collect Information | Outline how the learning will be presented, used and shared. | Update on progress per quarter | Provide any high level data per quarter | Provide any high level analysis per quarter | Update any conclusions or recommendations when learning activity completes
Effectiveness | Learning question 1: What factors contributed most to increased turnout at vaccination camps? | Post-activity surveys, FGD with CRPs | Quarterly | Presentation of Learning • Learning Briefs (1–2 pages) • Comprehensive Learning Report • PowerPoint Presentation for DHO & IHHN Stakeholders Use of Learning • Optimizing mobile camp site selection and CRP door-to-door mobilization schedules across 13 UCs. | Q1–Q4 Progress: 924 camps conducted, 3,383 children vaccinated. Key driver: CRP-led home visits prior to camp day. | High turnout correlated directly with female CRP door-to-door engagement in rural UCs. | CRP door-to-door advance notification should be institutionalized across all outreach camps.
Efficiency | Learning question 2: How cost-effective were the mobile vaccination activities compared to fixed sites? | Cost tracking, beneficiary comparison | Midline/Endline |  | Mobile outreach achieved 3x higher zero-dose child identification compared to static PHC visits in remote UCs. | Cost per vaccinated child in mobile camps was PKR 420 vs PKR 780 for static center transport support. | Mobile camps remain the most cost-effective mechanism for reaching zero-dose children in underserved UCs.
Community Engagement | Learning question 3: How effective were CRPs and social media in improving vaccine awareness? | KAP surveys, session feedback, SM analytics | Midline and Endline
Sustainability | Learning question 4 Are local health staff and structures able to maintain vaccination coverage post-project? | Exit interviews with PHC staff, DHO feedback | Final Evaluation
Adaptation | Learning question 5; What challenges emerged during integration into PHC and how were they addressed? | Monitoring reports, staff reflections | Quarterly
Sustainability & Integration | Learning Question 5: How effectively do Community Resource Persons (CRPs) transition demand generation and zero-dose identification to static Primary Health Care (PHC) facilities as project activities scale down during the extension period? | Exit interviews with PHC medical officers, CRP focus group discussions, facility-based immunization registration logs. | Quarterly (Q5–Q7) and Endline | Learning briefs presented to DHO & EPI coordinators to advocate for institutionalizing CRP honorariums into government health budgets. | Extension Baseline established (July 2026). | Tracking facility referral rates by CRPs across all 13 UCs. | To be completed at Endline (March 2027).
Equity & Security Navigation | Learning Question 6: What community-led adaptive strategies are most effective in maintaining zero-dose and under-immunized child coverage in security-sensitive or flood-prone UCs of Jhal Magsi? | Key informant interviews with local elders, CRP field diaries, GIS map tracking of reached vs unreached settlements. | Bi-annually (Q5 & Q7) | Shared with district EPI coordinators and emergency response teams to optimize mobile camp routing in hard-to-reach areas. | Tracking accessibility barriers in remote UCs. | Evaluating local elder mediation and weather-resilient scheduling. | To be completed in Q7 (March 2027).
Efficiency & Demand Generation | Learning Question 7: What is the relative cost-effectiveness and vaccine uptake efficiency of hybrid mobile camps compared to community mobilizer-led transport support to static PHC centers during the 9-month extension phase? | Cost tracking vs total vaccinated children/PLW data, caregiver satisfaction surveys. | Midline (Q6) and Final Evaluation (Q7) | Donor learning reports, policy briefs, and guidance notes for future NGO demand generation models in rural Balochistan. | Financial and coverage tracking active for Months 13–21. | Comparative analysis underway across 13 UCs. | Final report due March 2027.